## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29
Add check box to table | 7 | 5 | 3 | 0 | 0
Enable enrollment through check box | 3 | 3 | 3 | 0 | 0
Scrape subjects | 3 | 3 | 3 | 1 | 0
Search all subject | 4 | 4 | 4 | 4 | 0
Enable progress bar | 3 | 3 | 3 | 2 | 0
Testing | 4 | 4 | 4 | 4 | 4
Total hours | 24 | 22 | 20 | 11 | 4