## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29
Give filter checkbox suitable id | 4 | 0 | 0 | 0 | 0
Make filter checkbox functionable | 6 | 2 | 2 | 0 | 0
print filter result in console | 5 | 0 | 0 | 5 | 0
Design timetable elements | 0 | 8 | 0 | 0 | 0
make timetable responsive to enrollment | 3 | 3 | 7 | 2 | 0
Testing | 4 | 4 | 4 | 4 | 4
Total hours | 22 | 17 | 13 | 11 | 4